## Sheet1
Sligo Water System Meeting Minutes
BOARD OF COMMISSIONERS:
Cheryl McEntrye, Quentin Hunter, Tommy Strawn, Tammy Cates, Carol Ayres
2019-08-19
Members present: | Cheryl, Quetin, Tammy, Tommy & Carol
Member absent: | none
Agenda:
Meeting called to order by Cheryl at 6:04pm
Cheryl began speaking to the visitors that attended. She announced who were the board members
and Andy, as the licensed operator.
Quentin will discuss the systems history
Last meeting minutes were read out loud by Cheryl- Motion by Tommy approved, 2nd by Tammy
Financials:
Cheryl read over the financials-discussed what was on the bank statements up to end of July 2019.
Operations Account: $116,353.23
USDA Reserve Account: $78348.77
Capital Savings Account: $175563.68
Deposit Account: 15416.26
Quentin told about the history of the system: 2011 to present
*He & Cheryl had joined the board in 2011;
*Brown/Black water was a major issue at that time due to lack of flushing; Operator at the time
was saying he was flushing but wasn’t;
*Bridge over Red Chute: Repair crews hit the line crossing RC, causing brown water; A valve
was put in at the corner of CS, where parts of the system can now be closed off;
*Lines at Old River Place were found to have black water in joints-rerouting of the pipes
fixed that issue;
*Caplis Sligo bridge: repair crew hit the line, cost was substantial to fix, at which SWS had to pay for;
*NEW meters were installed that cost approx. $300-350 thousand and at that time, 50 to 60
meters were found where customers were not in the billing system, yet using the water;
*The inside of the water tank at the plant was cleaned out and the inside repaired-costing approx. $5000;
*Chemical room was repaired; Chemicals were changed over to bulk--savings were substantial;
*4 new fire hydrants were installed throughout the system at $3500 each;
*One booster pump motor was replaced at $3500; 4 new drives were installed at $17,000 to help save
on the life of the booster pumps. 2 well pumps were replaced at approx. $13,000
*USDA Reserve required $78,000 to be in an account at all times (this would pay the loan for one year)
it was not there until 2014, now has $78348.77 from November 2014 to present.
*There was no Capital savings account- now there has been one set up and it has $175563.68
*There was no Deposit account set up for the members- now there has been one set up and now has
$15416.26. Board stated that this was members money not theirs as the board.
*The board was looking at Bossier Parish to take over the system because it was broke in 2014.
*Andy came in as an interment operator in August 2014; A contract was signed in December 2014
and now SWS can sustain itself.
*All these changes and accounts have been implemented since Andy took over in 2014 to present.
Discussions:
*Board has options on the table for two new wells-- 1 at Caplis Sligo ball field; 3 from residentials, and
numerous other land owners are coming forward.
*Well site on Caplis Sligo at ball park: State wants a certified engineer to put in a system; not cost
effective, but will stay on the table as another source. It takes time to get the test results back from the lab,
then they will go to the engineer, where it usually takes approx. 20 days to get their
recommendations on how to treat the water. Test costs approx. $4000.
The original test showed water to be high in iron, so a filtration system will be needed.
*1 of the 3 residential sites has a small residential well already drilled on the property- Board agreed to
test that site first-
Member questions and comments:
*Members asked about communications between them and the board. Board stated that there
was a facebook page and also a website, and of course the monthly meetings, every 3rd Monday
of the month at Beulah Land baptist church at 6:00pm
*Members were asking about the connection to Bossier City water as it had been turned off on
August 7th. BC water was our emergency backup during the hot summer months. SWS only used
BC water for approx. 50 to 60 days a year but paid a minimum bill every month. There were some
members that didn’t want to be back on BC water for various reasons. BC has even pulled out the
pipe and valve. Members were told to talk to their Police Jury member to have them go to BC on
their behalf.
*Members asked about hooking up to Haughton water system on the other end of Sligo road.
Haughton Water was not an option, for they did not want to join up at this time.
*Members asked about a notifying them of a time line when the water levels would be back to
normal--Andy stated that he could not tell them anything--it was up to them to conserve as much
as they could right now.
*LDH performs a test themselves. That’s the $1 you pay every month on your bill… An arsenic test was
performed by LDH personnel. That person contacted SWS, said the test was messed up and needed
to be re-tested. Another test was performed and the results were normal. The original results
stated that there was a high volume of arsenic in the water and a letter was required to be mailed
out to every member on the system, however, SWS knew that the results were incorrect, and
did not mail out the letters. Also during this time, is when BC water was found with the ambioes.
Board did not want to alarm their members anymore than they had already been from the BC water,
at which time, parts of the SW system was on BC water. Failing to send out the letter, SWS was
was issued an AO violation. This AO can be beneficial if a loan is needed.
*Ball Park well: SWS paid to have an analysis test done. A filtration system is in the works, awaiting
the test results. The process for this plant to be up and going will take approx 2 years.
This well will provide Caplis Sligo approx. 500 homes. A land deal will be needed to be worked out.
SWS owns the well, but it is on Bossier Parish property.
*Residential wells-time frame 60 days
*Current tank level at 8ft--dangerous level at 4ft, system will shut down, until booster pumps
can get levels back up--at that time, the system will be under a boil advisory.
*BPPJ has been notified to stop watering the ball fields at night. They were still watering, causing
the tank levels to drop. Members asked if the ball field meters could be turned off. If they chose
to continue to water, then, yes they would be locked out. A data log test will be performed tonight
to see the usage.
*Billing software has been changed and now have a website. Sligowater.ruralwater.com
*Question was asked if something was to happen to Andy, what would happen to the system.
LRWA would step in with a temporary operator until Board could get another one.
*Member stated that they had calcium in there water heater. Andy stated that if they had a
whole home filteration system, that the filter was catching the chemical that was being used
to sequester and their filter was removing the chemical. He also stated that the system uses
a chemical to remove the high corrison factor in the pipes, and if you were using a filtration system,
that was altering the water quality that the system was providing.
*Member asked if a restriction plan could be implemented so no one else could get on the system.
By law, SWS can not deny anyone getting on the system.
*5 years ago, the situation the system was in, the board do not know how bad of shape
the finances were in, they trusted the operator. Now, safe guards have been put in place.
Andy is up front with all transactions with invoicing, addresses are trackable for work that has been
done. This board has no issues with Andy and his company.
*Future things are coming!!
*Next board meeting is set for Septemer 16th, Beulah Land Baptist Church @ 6pm
Adjourned by Quentin at 8:47pm
Respectfully,
Cyndy Freeman
2019-08-21